## Step 1 Budget
U.S. Department of Housing & Urban Development
Itemized Budget under FY2018 Comprehensive Housing Counseling Grant
Agency: | XXX Housing Agency |  |  | Grant #: | 0
Period Starting Date: | MM/DD/YYYY | Period End Date: | MM/DD/YYYY | Grant FY: | 0
Budget Items
a. Personnel (Direct Labor) |  | 10000
b. Fringe & Other Benefits |  | 3000
c. Training |  | 3000
d. Travel |  | 2000
e. Marketing and Outreach |  | 500
f. Other (Direct Costs) |  | 500
g. Subtotal of Direct Costs |  | 19000
h. Indirect Costs (approved indirect cost %) | 10% | 1900
Total Budget |  | 20900
Instructions
This worksheet serves to codify your budget.
1. Complete the yellow shaded areas with grant and agency information
2. Complete the blue shaded areas with your budget numbers.
*For definitions of budget line items, see the budget assumption tab
3. The green cells will calculate to show your total budget.

## Step 2 Plan
U.S. Department of Housing & Urban Development
Quarterly Planning
Agency: | XXX Housing Agency |  |  |  | Grant #: | 0
Period Starting Date: | MM/DD/YYYY | Period End Date: |  | MM/DD/YYYY | Grant FY: | 0
|  |  | Quarter 1 Expenditures |  | Quarter 2 Expenditures |  | Quarter 3 Expenditures |  | Quarter 4 Expenditures |  | Quarter 5 Expenditures |  | Quarter 6 Expenditures |  | Total Expenditures
Budget Items |  | Budget | percentage | dollars | percentage | dollars | percentage | dollars | percentage | dollars | percentage | dollars | percentage | dollars | percentage | dollars
a. Personnel (Direct Labor) |  | 10000 | 20% | 2000 | 20% | 2000 | 20% | 2000 | 20% | 2000 | 20% | 2000 | 0% | 0 | 100% | 10000
b. Fringe & Other Benefits |  | 3000 | 20% | 600 | 20% | 600 | 20% | 600 | 10% | 300 | 30% | 900 | 0% | 0 | 100% | 3000
c. Training |  | 3000 | 100% | 3000 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 3000
d. Travel |  | 2000 | 25% | 500 | 35% | 700 | 25% | 500 | 15% | 300 | 0% | 0 | 0% | 0 | 100% | 2000
e. Marketing and Outreach |  | 500 | 20% | 100 | 10% | 50 | 40% | 200 | 20% | 100 | 10% | 50 | 0% | 0 | 100% | 500
f. Other (Direct Costs) |  | 500 | 20% | 100 | 20% | 100 | 20% | 100 | 40% | 200 | 0% | 0 | 0% | 0 | 100% | 500
g. Subtotal of Direct Costs |  | 19000 |  | 6300 |  | 3450 |  | 3400 |  | 2900 |  | 2950 |  | 0 |  | 19000
h. Indirect Costs (approved indirect cost %) | 10% | 1900 |  | 630 |  | 345 |  | 340 |  | 290 |  | 295 |  | 0 |  | 1900
Total Budget |  | 20900 |  | 6930 |  | 3795 |  | 3740 |  | 3190 |  | 3245 |  | 0 |  | 20900
Instructions
This worksheet allows you to allocate your annual budget across the six quarters of your grant. You may want to allocate costs evenly (1/6 or 16.7% per quarter) or you may choose to more costs towards your early quarters. Some costs like training or equipment may be one time costs.
1. Complete the blue cells.
- Insert the percentage of the budget you expect to expend each quarter.
- Keep in mind, you may start spending your funds slowly and ramp up in the second quarter. Or, you may choose to expend all your funds over the first four or five quarters so so that you have little to spend in your final quarter.
- Note that the agency and budget information in the orange cells will self-populate with data from Step 1.
2. Check your work.
- The budget totals in the green cells will auto-calculate.
- Confirm that the percentages total 100 (in the first green column)
- Confirm the dollar amounts in the second green column equal the dollars in the orange budget column.

## Step 3 Record Actuals
U.S. Department of Housing & Urban Development
Budget Actuals vs Projections
Agency: | XXX Housing Agency |  |  |  | Grant #: | 0
Period Starting Date: | MM/DD/YYYY | Period End Date: |  | MM/DD/YYYY | Grant FY: | 0
|  |  | Quarter 1 Expenditures |  | Quarter 2 Expenditures |  | Quarter 3 Expenditures |  | Quarter 4 Expenditures |  | Quarter 5 Expenditures |  | Quarter 6 Expenditures |  | Total Expenditures |  | Grant funds
Budget Items |  | Budget | projected | actual | projected | actual | projected | actual | projected | actual | projected | actual | projected | actual | projected | actual | Remaining
a. Personnel (Direct Labor) |  | 10000 | 2000 | 1800 | 2000 | 2000 | 2000 | 2200 | 2000 | 2200 | 2000 | 0 | 0 | 0 | 10000 | 8200 | 1800
b. Fringe & Other Benefits |  | 3000 | 600 | 500 | 600 | 600 | 600 | 700 | 300 | 700 | 900 | 0 | 0 | 0 | 3000 | 2500 | 500
c. Training |  | 3000 | 3000 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 2500 | 500
d. Travel |  | 2000 | 500 | 500 | 700 | 500 | 500 | 600 | 300 | 500 | 0 |  | 0 | 0 | 2000 | 2100 | -100
e. Marketing and Outreach |  | 500 | 100 | 200 | 50 | 100 | 200 | 100 | 100 | 100 | 50 | 0 | 0 | 0 | 500 | 500 | 0
f. Other (Direct Costs) |  | 500 | 100 | 50 | 100 | 50 | 100 | 50 | 200 | 50 | 0 | 0 | 0 | 0 | 500 | 200 | 300
g. Subtotal of Direct Costs |  | 19000 | 6300 | 3050 | 3450 | 5750 | 3400 | 3650 | 2900 | 3550 | 2950 | 0 | 0 | 0 | 19000 | 16000 | 3000
h. Indirect Costs (approved indirect cost %) | 10% | 1900 | 630 | 305 | 345 | 575 | 340 | 365 | 290 | 355 | 295 | 0 | 0 | 0 | 1900 | 1600 | 300
Total Budget |  | 20900 | 6930 | 3355 | 3795 | 6325 | 3740 | 4015 | 3190 | 3905 | 3245 | 0 | 0 | 0 | 20900 | 17600 | 3300
Instructions
This worksheet allows you to track your actual costs each quarter and see how much money remains to be expended over the remaining grant period.
1. Complete the blue cells.
- Enter the actual expenditures for the grant quarter by category.
- Note that the agency information and budget projections in the orange cells will self-populate with data from Step 2.
2. Assess your status.
- The total actual l expenditures and remaining funds in the green cells will auto-calculate.
- Compare your quarterly actuals to your projections to see if you are spending your funds as planned.
- If you are running ahead or behind on the quarter, consider how you can adjust in future quarters.
- Look at the total funds remaining in the green column. Confirm that the totals are positive. If they are negative, you may have to do some rebudgetting.
- If you have concerns about your budget, go to step 4 for additional analysis.
Note on A14: HUD User: Marketing/Outreach

## Step 4 Analysis
U.S. Department of Housing & Urban Development
Budget Analysis
Agency: | XXX Housing Agency |  |  |  | Grant #: | 0
Period Starting Date: | MM/DD/YYYY | Period End Date: |  | MM/DD/YYYY | Grant FY: | 0
|  |  | Year to Date Expenditures |  | Remaining |  | Notes
Budget Items |  | Budget | Actuals | Remaining | quarters | $/quarter | On budget?
a. Personnel (Direct Labor) |  | 10000 | 8200 | 1800 | 2 | 900
b. Fringe & Other Benefits |  | 3000 | 2500 | 500 | 2 | 250
c. Training |  | 3000 | 2500 | 500 | 2 | 250
d. Travel |  | 2000 | 2100 | -100 | 2 | -50
e. Marketing and Outreach |  | 500 | 500 | 0 | 2 | 0
f. Other (Direct Costs) |  | 500 | 200 | 300 | 2 | 150
g. Subtotal of Direct Costs |  | 19000 | 16000 | 3000 | 2 | 1500
h. Indirect Costs (approved indirect cost %) | 10% | 1900 | 1600 | 300 | 2 | 150
Total Budget |  | 20900 | 17600 | 3300 | 2 | 1650
Instructions
This worksheet helps you assess if you are on pace to spend your budget by the end of the grant period.
1. Complete the blue cells.
- Insert the number of quarters remaining in your grant period. For example, if you inserted data for Q2, you have 4 quarters remaining.
- Note that the agency information, budget, actuals, and remaining funds in the orange cells will self-populate with data from Step 3.
2. Assess your status.
- The budget available per quarter for the remaining quarters in the green cells will auto-calculate.
- Confirm that you are on pace to spend that amount quarterly through the end of the grant period.
- Make any notes about the status of your budget. E.g. Do you need to speed up expenditures or slow them down? Is rebudgetting necessary?

## Appendix - budget assumptions
Line Item | Cost Principle Considerations | Assumption Examples
Personnel | Rates are reasonable, meet grant requirements for experience, within executive compensation requirements, §200.430 Compensation: Personal Services | Name, pay rate, labor category, # of hours and housing counseling years of experience.
Fringe Benefits | Reasonable rate, allowable fringe pool, §200.431 Compensation—Fringe Benefits. | Fringe pool (accounts), rate and effective date.
Training | Allowable under §200.474 Training and Education and §200.432 Conferences | Purpose of training, rates, # of hours/fixed fee and services provided.
Travel | Reasonable (consistent with Federal Travel Regulations “FTR”), allowable purpose, allocable for HUD/OHC related activities, §200.474 Travel Costs | Purpose of travel, # of participants and itemized costs. ALL travel must be approved by HUD in advance of travel.
Marketing and outreach | Allowable, allocable for HUD/OHC related activities, reasonable costs/quantity | Itemized list (including quantity, unit, rate), use/purpose and costs.
All other proposed Costs incurred as part of eligible activities | Allowable under Omni Circular Subpart E, allocable for HUD/OHC related activities, reasonable and necessary | Rationale/justification, costs, allocation methodology and purpose.
Indirect Costs | Allowable under §200.414, includes costs associated with operating and maintaining buildings and facilities, and general administration and general expenses, such as the salaries and expenses of executive officers, personnel administration, and accounting. | Federal Agency Acceptance of negotiated rate or the de Minimis rate (10% of Modified Total Direct Costs).